## BUDGET
Wedding Budget - Enter total budget below
30000
| Total quote | Paid so far | Balance due | Balance due date | Paid by groom | Paid by parents | Paid by bride | Notes
Stationery
Invitations | 0 | 0 | 0
Postage costs | 0 | 0 | 0
Programs | 0 | 0 | 0
Thank you letters | 0 | 0 | 0
Subtotal | 0 | 0 | 0
Budgeted 2% | 600
Flowers/Decorations
Attendants' bouquets | 0 | 0 | 0
Reception | 0 | 0 | 0
Groomsmen | 0 | 0 | 0
Subtotal | 0 | 0 | 0
Budgeted 2% | 600
Photography/Videographer
Wedding photographer | 0 | 0 | 0
Video | 0 | 0 | 0
Subtotal | 0 | 0 | 0
Budgeted 6% | 1800
Music
Ceremony quartet | 0 | 0 | 0
Live band or DJ | 0 | 0 | 0
Subtotal | 0 | 0 | 0
Budgeted 5% | 1500
Catering/Event Location
Reception site fee | 0 | 0 | 0
Drinks | 0 | 0 | 0
Food | 0 | 0 | 0
Staff dinners | 0 | 0 | 0
Wedding Cake | 0 | 0 | 0
Lighting | 0 | 0 | 0
Wishing well | 0 | 0 | 0
Subtotal | 0 | 0 | 0
Budgeted 45% | 13500
Attire
Wedding Dress | 0 | 0 | 0
Headpiece and Veil | 0 | 0 | 0
Shoes | 0 | 0 | 0
Jewellery | 0 | 0 | 0
Hair | 0 | 0 | 0
Makeup | 0 | 0 | 0
Tan | 0 | 0 | 0
Nails | 0 | 0 | 0
Groom suit and tie | 0 | 0 | 0
Groom shoes | 0 | 0 | 0
Subtotal | 0 | 0 | 0
Budgeted 15% | 4500
Gifts
Bridesmaids | 0 | 0 | 0
Groomsmen | 0 | 0 | 0
Guests | 0 | 0 | 0
Subtotal | 0 | 0 | 0
Budgeted 4% | 1200
Transportation/Accommodations
Wedding cars | 0 | 0 | 0
Wedding Night Suite | 0 | 0 | 0
Subtotal | 0 | 0 | 0
Budgeted 9% | 2700
Misc Fees
Church or Ceremony location fees | 0 | 0 | 0
Wedding Rings | 0 | 0 | 0
Church bells | 0 | 0 | 0
Dance lessons | 0 | 0 | 0
Subtotal | 0 | 0 | 0
Budgeted 12% | 3600
Total budget | 30000
Total cost so far | 0
Total paid so far |  | 0

## WEDDING GUEST LIST
Guest list
Guest Name | Address | RSVP YES | Dietry Requirements | RSVP NO | Invitation Count
Bride |  | 1
Groom |  | 1
TOTALS |  | 2 |  | 0 | 0

## BRIDAL PARTY CONTACT INFO
Bridal Party Contact Info
Name | Address | Role in Wedding | Home Phone | Mobile Phone | Email | Out of State? | Child under 12?

## SUPPLIER LIST
Suppliers
Supplier Type | Supplier Name | Contact Name | Address | Email | Phone | Fax | Notes
Florist
Reception
Officiant
Band
String Quartet
MC
Jeweller
Cars
Bridal Shop
Photographer
etc……

## WHO IS DOING WHAT
Who's Doing What on “The Day”
Name | Role | Contact details | Notes
This sheet is used to keep track of things people are doing on the day of.
Example: Who is responsible for taking your gifts home? Who is setting up the centerpieces?
Who is taking the centerpieces home? Who is bringing home the guestbook?

## TIMELINE
Wedding Day Timeline of Events
Activity | 11:00 | 11:15 | 11:30 | 11:45 | 12:00 | 12:15 | 12:30 | 12:45 | 13:00 | 13:15 | 13:30 | 13:45 | 14:00 | 14:15 | 14:30 | 14:45 | 15:00 | 15:15 | 15:30 | 15:45 | 16:00 | 16:15 | 16:30 | 16:45 | 17:00 | 17:15 | 17:30 | 5:45 | 18:00 | 18:15 | 18:30 | 18:45 | 19:00 | 19:15 | 19:30 | 19:45 | 20:00 | 20:15 | 20:30 | 20:45 | 21:00 | 21:15 | 21:30 | 21:45 | 22:00 | 22:15 | 22:30 | 22:45 | 23:00 | 23:15 | 23:30 | 23:45 | 0:00
1. Pre-Wedding Activities 1pm – 4:30pm
1a. Pre-Wedding Activity: Girls 12:00pm – 4:30pm
Reception Center Open for All Vendors | [8 empty] | 1:00pm – 12:00am
Girls arrive and are in Bride's room getting ready | 9:00am – 3:00pm
Lunch available for girls |  |  |  |  | 12:00pm – 1:00pm
Hairdresser 1 Arrives | 9:00am – 3:00pm
Hairdresser 2 Arrives | 9:00am – 3:00pm
Makeup Artist Arrives | 9:00am – 3:00pm
Girls hair and makeup | 9:00am – 3:00pm
Bride's hair | [5 empty] | 12:00pm – 1:00pm
Bride's Makeup | [9 empty] | 1:00pm – 2:00pm
Photographer arrives to take photos of girls getting ready | [10 empty] | 1:30pm – 2:00pm
Bride put dress on and do final adjustments | [14 empty] | 2:30pm – 3:00pm
Videographer Begins | [14 empty] | 2:30pm.
Videographer visits girls in room | [14 empty] | 2:30pm – 3:00pm
LIMOS 1&2 Arrive at Hotel and is on duty | [18 empty] | 3:30pm.
Girls take Pictures outside Hotel | [16 empty] | 3:00pm – 3:45pm
Photographer leaves girls and drives to Reception | [19 empty] | 3:45pm.
Girls freshen up in limo | [19 empty] | 3:45pm – 4:00pm
LIMOS 1&2 leaves Hotel with girls and drives to Reception | [20 empty] | 4:00pm – 4:30pm
Girls Arrive at the Reception | [21 empty] | 4:15pm.
Out of BUS 1 and prepare to walk down aisle | [22 empty] | 4:30pm.
1a. Pre-Wedding Activity: Guys 1:30pm – 4:30pm
Boys arrive and are in Groom's room getting ready | [6 empty] | 12:30pm – 3:00pm
Lunch available for boys | [6 empty] | 12:30pm – 12:45pm
BUS 2 Arrives at Hotel & is on duty | [16 empty] | 3:00pm.
Guys walk down to BUS 2 | [16 empty] | 3:00pm.
BUS 2 Leaves Hotel, takes guys, and Drives to Piedmont CC | [16 empty] | 3:00pm.
Guys arrive at the Hall | [19 empty] | 3:45pm.
Guys take candid photos with assistant photographer | [17 empty] | 3:15pm.
Videographer visits guys at Reception Hall | [20 empty] | 4:00pm – 4:30pm
Guys put programs | [20 empty] | 4:00pm – 4:30pm
Guys are ushering guests in | [20 empty] | 4:00pm – 4:30pm
1c. Pre-Wedding Activity: Vendor/Event Set-up/Shuttle 1:00pm – 4:00pm
Facility Rental timeframe | [8 empty] | 1pm – 12am
Florist arrives and decorates | [8 empty] | 1pm – 4pm
Caterer Arrives | [8 empty] | 1pm – 4pm
Band arrives and sets-up | [8 empty] | 1pm – 4pm
Band sets-up ceremony PA system and handheld mics
Band sets-up dinner PA system (outside the Reception Hall)
Carol Alban Trio arrives and sets-up | [16 empty] | 3:00pm – 4:00pm
BUS 2 Arrives at Hotel to take hotel guests to Reception Hall | [19 empty] | 3:45pm – 4:15pm
BUS 2 Arrives at Reception Hall with Hotel guests | [21 empty] | 4:15pm.
Cake is delivered to Reception Hall | [10 empty] | 1:30pm – 3:30pm
Florist delivers bouquets and boutineers to the Hote | [8 empty] | by 2:00pm
Florist decorates the ceremony and reception site with flowers/petals | [8 empty] | 1pm – 4pm
Florist decorates the ceremony site with fresh rose petals down the aisle
Florist to put sprig of rosemary on every placesetting | [8 empty] | 1pm – 4pm
Florist set-up floral centerpieces | [8 empty] | 1pm – 4pm
Florist to put out urns at ceremony location | [8 empty] | 1pm – 4pm
Florist to put out floral garland at ceremony locations | [8 empty] | 1pm – 4pm
Florist to spinkle petals on inside reception facility cocktail tables | [8 empty] | 1pm – 4pm
Florist to sprinkle petals on cake table | [8 empty] | 1pm – 4pm
Florist to put out centerpieces on rect. dinner tbl, bathroom, 2 guestbook, tble by bath | [8 empty] | 1pm – 4pm
Florist to fill the urns inside the hall with flowers | [8 empty] | 1pm – 4pm
Wedding Coordinator to pick up items from Bride and Groom's house | [5 empty] | 12pm – 1pm
Wedding Coordinator set-up apple centerpieces with pink water | [8 empty] | 1pm – 4pm
Wedding Coordinator set-up apple placecards | [8 empty] | 1pm – 4pm
Wedding Coordinator set-up guest book table | [8 empty] | 1pm – 4pm
Wedding Coordinator set-up camera on tables | [8 empty] | 1pm – 4pm
Wedding Coordinator set-up tuele ring ceremony fixtures | [8 empty] | 1pm – 4pm
Wedding Coordinator set-up ring ceremony ribbon | [8 empty] | 1pm – 4pm
Wedding Coordinator to set-up brown overcloth on cake table | [8 empty] | 1pm – 4pm
Wedding Coordinator to set out cake knife and server | [8 empty] | 1pm – 4pm
Wedding Coordinator to set-up photo easles inside and outside reception hall | [8 empty] | 1pm – 4pm
Wedding Coordinator to set-up rose petals at the ceremony location | [8 empty] | 1pm – 4pm
Wedding Coordinator to set-up rice bags at the ceremony location in inner aisle seats | [8 empty] | 1pm – 4pm
Wedding Coordinator to set-out bar menu on bar (2) | [8 empty] | 1pm – 4pm
Wedding Coordinator to put out the menu cards on each placesetting | [8 empty] | 1pm – 4pm
Wedding Coordinator to set-up toasting goblets at headtable | [8 empty] | 1pm – 4pm
Wedding Coordinator and caterer to work together to put flashlights under the cocktail tables | [8 empty] | 1pm – 4pm
Wedding Coordinator to hang the tealight lamps in the tree in the center of the outside reception area | [8 empty] | 1pm – 4pm
Wedding Coordinator to set-up table name cards (three apples in vase, pink water, and stick with namecard | [8 empty] | 1pm – 4pm
Caterer to take one cocktail table to the ceremony site for the unity candle and put brown cloth on
Caterer to set-up tableclothes indoor and outdoor | [8 empty] | 1pm – 4pm
Caterer to set-up tea-light lamps inside reception area on tables | [8 empty] | 1pm – 4pm
2. Ceremony 4:30pm – 5:00pm
String Quarter Plays | [21 empty] | 4:00pm – 7:00pm
Groom comes out | [22 empty] | 4:30pm.
Ceremony “start” time | [22 empty] | 4:30pm.
Walk Down the Aisle | [22 empty] | 4:30pm.
3. Cocktail Hour/Photos 5:00pm – 6:00pm
Photos | [24 empty] | 5:00pm – 6:00pm
Cocktail and Hor'deourves Hour | [24 empty] | 5:00pm – 6:00pm
String Quartet Ends | [30 empty] | end time
4. Reception 6:30pm – 11:00pm
Bridal party heads to reception | [28 empty] | 6:00pm.
Bridal Party announced in by Band | [29 empty] | 6:15pm.
Toast, after dinner – Band to handle mics | [31 empty] | 6:50pm.
String Quarter Ends | [31 empty] | end time
Dinner is served | [29 empty] | 6:15pm –7:15pm
Vendors meals are available | [29 empty] | 6:15pm –7:15pm
Ambient Music to be played via CD outside by PushPlay | [29 empty] | 6:15pm –7:15pm
Dancing | [33 empty] | 7:15pm – 10:15pm
Band Announces First Dance | [33 empty] | 7:15pm – 8:00pm
Band Announces Father/Daughter Dance | [33 empty] | 7:15pm – 8:00pm
Band Announces Bridal Party Dance | [33 empty] | 7:15pm – 8:00pm
Open Dancing | [33 empty] | 7:15pm – 8:00pm
Band Takes Break | [36 empty] | 8:00pm –8:15pm
Band Announces Cut the cake | [37 empty] | 8:15pm –8:20pm
Round 2 of Dancing | [37 empty] | 8:15pm – 9:00pm
Band Takes Break | [40 empty] | 9:00pm –9:15pm
Round 3 of Dancing | [41 empty] | 9:15pm –10:00pm
Band Announces Bouquet and Garter Toss | [41 empty] | 9:15pm –10:00pm
Videographer Off Duty | [46 empty] | 10:30pm.
Band Ends | [47 empty] | 10:45pm.
Groom and Bride leave via Limo | [48 empty] | 11:00pm.
Party's Over! | [48 empty] | 11:00pm.
Vendor Clean-up | [48 empty] | 11:00pm – 12:00am
BUS 1 Arrives to shuttle people to Hotel | [43 empty] | 9:45pm.
BUS 1 Arrives to shuttle people to Hotel | [45 empty] | 10:00pm.
BUS 1 Arrives to shuttle people to Hotel | [47 empty] | 10:45pm.
BUS 1 Off Duty | [47 empty] | 11:00pm.
Exit Hall | [52 empty] | midnight
5. Break Down and Clean Up 11:00pm – 12:00am
Caterer Clean-up | [48 empty] | 11:00pm – 12:00am
Band Clean-up | [48 empty] | 11:00pm – 12:00am
Exit Facility | [52 empty] | midnight

## TO DO LIST
To-Do List
Planning Phase | Timeframe | Category | Sub Category | Item Description | Action | Category | Owner | Due Date | Completed (YES or NO)
Phase 1: Just Beginning | 3-9 Months To Go! | Bridal Luncheon | Bridal Luncheon | Plan the bridal luncheon (pick a place, gather guest list) | Call and Reserve | Hotel Lunch |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Beauty/Hair/Makeup | General Beauty | Experiment with your beauty routine (ie: self-tanners, skincare, facials, etc..) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Music | Music | Check out amplified music restrictions at your venue. |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Unity Candles | If getting married outside figure out a way to light the candles without them blowing out (put the into a large vase or hurricane) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Furniture Set-up | Design where the tables will be placed in the reception area, how the chairs will be set-up at the ceremony (if you have a choice) | Plan | Planogram |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Unity Candles | Figure out how you will light them (pretty wedding aim-n-flame, etc.) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Disposable Cameras | Purchase disposable cameras | Buy/Shop | décor |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Hotel for Guests/Wedding Night | Wedding Night | Book hotel room for you and your guy for your Wedding Night | Call and Reserve | Hotel |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bridesmaids | Begin to shop for the bridesmaid dresses. Plan a day to take your gals shopping. |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Music | Music | Create the songs list for muscians | Plan | Music |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Beauty/Hair/Makeup | Dentist | Go to the dentist for a cleaning. Ask about whitening services. |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Groomsmen/Fathers | Have the guy's submit their sizes to the retailer/renter |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Groom | Select and Purchase/Rent the Groom's accessories he will need: shoes, shirt stays, cufflinks, and a pocket square | Buy/Shop | Brian's Tux |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Groom | Select and Purchase/Rent the Groom's Tux/suit – place order |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Ceremony | Ceremony | Meet with Officiant for ceremony | Call and Reserve | Officiant |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Table Names/Numbers | Design how the Table Numbers will be displayed |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Limo | Limo | Research and book a limo company |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Signage | Design signage for guest shuttles from the hotel to the wedding (include pick up times, etc) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Venue | Venue | Research venues for reception and ceremony |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Ceremony Programs | Design Wedding Program |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Groomsmen/Fathers | Select the Groomsmen's and Fathers' tux/suit – place order | Confirm | Tuxedos |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bride | Schedule first fitting and final fitting | Attend/Make Appt. | Wedding Dress |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Wedding Rings | Wedding Rings | Shop for & purchase wedding bands (send them out for engraving, but make sure they’ll be back in time for the ceremony) | Buy/Shop | Rings |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Unity Candles | Get/Make/Buy table covering for the unity candle display table – hurricane shade, etc | Buy/Shop | Ceremony |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Gifts for People | Gifts for People | Find & purchase bridal party attendants gifts | Buy/Shop | Gifts |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Wedding Invitations | Purchase your Wedding Invitations | Buy/Shop | Stationary |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Favors | Purchase/Make your favors |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Flowergirl | Begin to clip out magazine clippings of your favorite dresses. Share them with your lil' gal or gals! Unlike your bridesmaids they will usually love everything you pick! |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Videographer | Videographer | Research and book a videographer |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bride | Buy any special lingerie your gown requires prior to first fittings | Buy/Shop | Wedding Dress |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Rehearsal and Rehearsal Dinner | Ceremony Rehearsal | Book the ceremony venue for the rehearsal. Sometimes they allow you to have it the day before, but sometimes you have to pick another day. |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Gift Registry | Gift Registry | Let folks know where you registered by word of mouth or put it in the shower invite. Keep in mind it's VERY bad taste to put registry info into your actual wedding invitation. |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Flowergirl | Confirm the delivery date of the flowergirl dresses (some dress makes require 3 months lead-time) | Confirm | Bridal Party |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Rentals | Reserve rental items needed for ceremony and reception | Call and Reserve | Caterer |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Wedding Cake | Wedding Cake | Book a baker |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Mothers' Attire | Take a day and go shopping with your Mom's. Make it special – take her to lunch and have a blast! | Plan | Mother's Fashion |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Gift Registry | Gift Registry | Select your favorite retailers and go register! If your guy isn't gung-ho have him go to just one store with you – then invite your mom/friend to go with you and register at the rest. Girls have way more fun shopping! |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Hotel for Guests/Wedding Night | Hotel for Guests | Research hotels for out-of town guests to stay at – Schedule a block of rooms | JDI (Just Do It) | Guest Count |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Mothers' Attire | Confirm delivery date for dress. (some dress makers requires 3 months lead time) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Mothers' Attire | Make final dress selection and place order |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Flowers | Place final order with florist | Attend/Make Appt. | Florist | susan and stacey – thursday |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Flowergirl | Make final dress selection and notify her mom of how to send in sizes, etc. |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Flowergirl | Purchase flowergirl dresses | Buy/Shop | Flowergirls |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Music | Music | If possible, go listen to the band play at another event |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Flowergirl | Plan a day to take your lil' gal out – make it all about her. Maybe even do her hair and makeup before. Go shop for dresses! |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Ring Pillow | Purchase your Ring Pillow | Buy/Shop | Wedding Accessories |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Rose Petals | Buy fake rose petals to see what they look like – or order real ones | Buy/Shop | Wedding Accessories |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Signage | Assign a vendo/person to put out all signage for ceremony and reception | Assign to Vendor | Signage | Kerri will do |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bride | Pick “THE” dress and place your order (some designers require at least 6-9 months lead time when ordering) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bridesmaids | Make sure attendants have purchased their dresses | Confirm | Bridal Party |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Table Names/Numbers | Figure out what the names of the tables will be (Love table, Tahoe table, etc.) | Design and Create | décor |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bridesmaids | Make final dress selection and notify your gals of the dress choice (how to send sizes in, payment, etc) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Ceremony | Ceremony | Write your vows (if you are doing that) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bridesmaids | Select bridesmaid shoes and let your gals know how to order | Buy/Shop | Bridal Party |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Signage | Design entry signage for ceremony and reception (if needed) | Design and Create | Signage |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bridesmaids | Confirm the delivery date of the bridesmaid dresses (some dress makers require at least 3 months lead time) | Confirm | Bridal Party |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bridesmaids | Begin to clip out magazine clippings of your favorite dresses. Share them with your gals – if they don't like your choices say “though sh&t” and make them wear orange tafetta with a matching parasol. |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Beauty/Hair/Makeup | Hair | Gather magazine clippings for how you want to do your hair | Research | Hair |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bride | Begin to break-in your shoes | JDI (Just Do It) | Wedding Dress |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Photo Displays | Design and build a way to display photographs during reception of you and your man and family and friends | Design and Create | décor |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Powder Room Basket | Design/Select Items for Powder Room Basket |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Rehearsal and Rehearsal Dinner | Rehearsal Dinner | Mail invitations to rehearsal dinner (traditionally done by parent's of the groom) | Mail | Rehearsal Dinner |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bride | Start the hunt for the perfect gown. Begin clipping out magazine photos! |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bride | Purchase wedding dress accessories (shoes, lingerie, etc..) | Buy/Shop | Wedding Dress |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Rehearsal and Rehearsal Dinner | Rehearsal Dinner | Reserve rehearsal dinner location (traditionally done by parent's of the groom) | Call and Reserve | Rehearsal Dinner |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bride | Purchase veil and hair jewelry | Buy/Shop | Wedding Dress |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Mothers' Attire | Let your Mom's know what color you'd like them to wear |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Music | Music | Research bands/DJ's and call to speak with them |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Honeymoon | Honeymoon | Get online or talk to a travel agent about your honeymoon. Book it as soon as you decide. |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Venue | Venue | Make sure your décor is OK with the venue. Sometimes they restrict candle use, etc. |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Venue | Venue | Book your Venue |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Placecards | Design how the placecards will be done (already on the dinner table with a sign to tell them where they sit OR on a separate table where they go pick them up then go to their seat) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Centerpieces | Purchase supplies for your centerpieces |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Ceremony | Ceremony | Research unique ceremony traditions and adapt your favorites to you own ceremony | Design and Create | Ceremony |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Hotel for Guests/Wedding Night | Hotel for Guests | Let guests know about the hotel (Rates, how to book, etc). You can put this info in your invitations or on your website. |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Beauty/Hair/Makeup | Makeup | Gather magazine clippings for how you want to do your makeup | Research | Hair |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Flowers | Design your floral scheme, and negotiate prices with florist | Attend/Make Appt. | Florist |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Signage | create signage for ceremony and reception | Design and Create | Signage | stacey and susan |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Photography | Photography | Research and book your favorite photographer |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Guest Book | Design how the Guest Book table will be set-up (special linens, candles, flowers, signage) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Caterer | Caterer | Make final decision on caterer to use, as soon as possible |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Venue | Venue | Call Venue Manager and get a list of all available furniture and a floor plan if they have it |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Caterer | Caterer | Call various caterers to see what they're about (menus, pricing, services offered) | Attend/Make Appt. | Caterer |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Guest Book | Purchase your Guest Book and Special Pen | Design and Create | Guest Book |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Flowergirl | Select flowergirl shoes and submit the order | Buy/Shop | Bridal Party |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Dress/Tux/Bridal Party | Bride | Make a date with your mom/family/friends to go help you try on gowns – make it a whole day of fun! |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Unity Candles | Design how the Unity Candle table will be set-up (special linens, candles, flowers) |  |  |  |  | NO
Phase 1: Just Beginning | 3-9 Months To Go! | Decor/Invitations/Programs/etc. | Wedding Invitations | Design/Shop around for your Wedding Invitations |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Beauty/Hair/Makeup | Hair | Schedule and go to hair trial | Attend/Make Appt. | Hair |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Honeymoon | Honeymoon | Buyyour honeymoon wardrobe! Buy lot's of sassy lingerie... you pussy cat, you! | Buy/Shop | Honeymoon |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Wedding Invitations | Plan a Wedding Invitation Party with your family and friends to stuff, address,lick, stamp, and prep the invitations to be mailed |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Ceremony | Ceremony | Decide how and who will pass out the programs and tell them that at the rehearsal | Plan | Programs |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Photo Displays | Assign someone the task of taking the photo displays to the reception site |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Hotel for Guests/Wedding Night | Hotel for Guests | Call the hotel and see how many people have booked – keep record in case you need to remind some folks to get a reservation. |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Mothers' Attire | Pick up dress and get alterations if needed. |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Placecards | Write/Print names on Placecards |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Signage | Assign someone the task of bringing the signage (easles) home after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Rose Petals | Assign someone the task of sweeping up the rose petals after ceremony (vendor) | Assign to Vendor | Rose Petals | Kerri will do |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Unity Candles | Assign vendor with task of putting overclothes on the tables | Assign to Vendor | décor | caterer |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Photography | Photography | Pick the photo site for the girls photos before the wedding and guys' photos | Research | Photographer |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Photography | Photography | Prepare a must take photo list naming important family members and guests | Design and Create | Photographer |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Signage | Assign someone the task of taking the signage to the hotel and setting it up |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Bridesmaids | Remind bridesmaids where they can pick up their dresses (make sure everything fits properly or get alternations) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Rehearsal and Rehearsal Dinner | Rehearsal Dinner | Finalize rehearsal dinner plans, order rehearsal invitations, menus, table numbers, (traditionally done by parent's of the groom) | Confirm | Rehearsal Dinner |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Bridal Luncheon | Bridal Luncheon | Send out invitations or just let your gals know when it is. | Call and Reserve | Spa Day |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Signage | Print out signage for guest shuttles from the hotel to the wedding (include pick up times, etc) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Powder Room Basket | Purchase items for Powder Room Baskets |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Powder Room Basket | Assign someone to take the Powder Room Basket to the reception site and set it up in the powder room |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Bride | Shop for and buy Rehearsal Dinner outfit |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Wedding Invitations | Take the invitations to the post office and have them “hand canceled” w/ a rubber stamp instead of my machine. It looks nicer. |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Flowergirl | Remind your flowergirl's mom where she can pick up the dresses (make sure everything fits properly or get alternations) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Everything | Plan a “craft day” party with your family and friends so they can help you put everything together! |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Beauty/Hair/Makeup | Makeup | Schedule and go to makeup trial | Attend/Make Appt. | Makeup |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Schedule/Plan-o-Gram/Seating | Timeline | Create a detailed schedule of events/timeline for the entire wedding day (include prep time) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Music | Music | Finalize “must play” and “do not play” list with Band |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Rehearsal and Rehearsal Dinner | Rehearsal Dinner | Keep a log of RSVPs (traditionally done by parent's of the groom) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Photo Displays | Purchase Supplies/Make your photo displays |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Photo Displays | Assign someone the task of bringing the photo displays home after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Table Names/Numbers | Assign someone the task of bringing the table names/numbers to the reception |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Guest Book | Assign someone the task of bringing the guest book and pen home after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Legal |  | Go get marriage license, bring valid drivers license | Attend/Make Appt. | License |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Ceremony | Ceremony | Finalize the “show-flow” of your ceremony (what happens when, who does what, what music plays when, etc.) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Ceremony | Ceremony | Assign someone (Maid of Honor/Best Man) the task of bringing home the marriage certificate |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Ceremony | Ceremony | Find “something old, new, borrowed, blue” | Research | Old/New/Borrowed/Blue |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Wedding Invitations | Take a wedding invitation to the post office and have it weighed to make sure you buy enough postage |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Centerpieces | Assign someone the task of bringing the centerpieces to the site and setting them up (oftentimes the caterer will do this) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Disposable Cameras | Assign someone the task of bringing the cameras home after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Centerpieces | Design your centerpieces |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Centerpieces | Assign someone the task of bringing the centerpieces home after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Ceremony Programs | Assign someone the task of bringing the left-over Programs home after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Ceremony Programs | Assign someone the task of bringing the programs and getting them to the ushers on the day-of |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Flowergirl | Confirm with your flowergirl's mom that she has her dress and everything fits. | Confirm | Wedding Dress |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Ceremony | Ceremony | Finalize ceremony readings or other traditions you will have during your ceremony. Notify everyone involved. | Confirm | Ceremony | stacey |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Wedding Invitations | Mail your Invitations – 8 weeks before your event |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Groom | Call and confirm the order (if renting) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Wedding Invitations | Wedding Invitations | Keep log of RSVPS |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Bridesmaids | Purchase lipstick, nail polish, etc you want bridesmaids to wear |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Welcome Baskets | Assign someone the task of taking the Welcome Baskets to the Hotel one day prior to your first guests arrival |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Bridesmaids | Select your gals accessories (jewels, etc). This is traditionally a gift you can give your gals. |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Caterer | Caterer | Finalize menu, beverage, and alcohol order with caterer | Confirm | Caterer |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Roles for People |  | Assign someone to take the gifts back to my home | Assign to Family | Transport of Items | chuck and shirley |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Ring Pillow | Assign someone the task of bringing the pillow to the reception site and getting it to the Ring Bearer (or ring bearer's parent) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Roles for People |  | Notify family/friends whom you would like to give readings, sing solos, serve as guest book attendant, etc.. | Plan | Ceremony |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Roles for People |  | Prepare “Wedding Party Responsibility” Cards |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Caterer | Caterer | Schedule tasting with caterer you selected | Attend/Make Appt. | Caterer |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Table Names/Numbers | Assign someone the task of bringing the table names/numbers home after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Schedule/Plan-o-Gram/Seating | Plan-o-Gram | Create a plan-o-gram (Furniture set-up) for the ceremony, reception hall, guest book area, etc) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Welcome Baskets | Coordinate with the hotel how/if they will pass these out for you when guests arrive or put them in their rooms |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Newspaper | Your Announcement | Check with newspaper for wedding announcements | Research | Newspaper |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Welcome Baskets | Assign someone the task of bringing home left-over Welcome Baskets home from the hotel or just give them to the hotel staff |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Gift Registry | Gift Registry | Check that there are enough options left on your registry | Confirm | Registry |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Venue | Venue | Send the Venue Manager your desired furniture set-up |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Thank You's and Gifts | Gifts | Create a card box to be displayed on your gift table so that if folks brought a card it can be slipped into the box rather than just laying on the table (could have money in it, etc) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Guest Book | Assign someone the task of taking the guest book and pen to the reception site |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Flowers | Confirm delivery times, locations, and final arrangement count with florist |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Venue | Venue | Schedule walk-thru's with your vendors if they have never worked at this venue before |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Furniture Set-up | Communicate your furniture set-up design (plan-o-gram) to the ceremony and reception location |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Venue | Venue | Finetune facility rental timeframe | Confirm | Piedmont CC |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Unity Candles | Assign someone the task of taking the Unity Candle to the ceremony site and setting up the table display |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Unity Candles | Purchase your Unity Candles |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Unity Candles | Assign someone the task of bringing the Unity Candle home after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Gifts for People | Gifts for People | Wrap all gifts for the wedding party and write them a nice note |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Gifts for People | Gifts for People | Find and purchase parents gifts | Buy/Shop | Gifts |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Groomsmen/Fathers | Remind groomsmen/fathers where they can pick up their attire (make sure everything fits properly) |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Favors | Assign someone the task of taking the favors to the reception site |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Rentals | Arrange for someone to return rental items after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Disposable Cameras | Author, design and print the table camera to-do lists to explain to people what you'd like pictures of | Design and Create | décor | Kerri |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Disposable Cameras | Assign someone the task of bringing the cameras to the site and setting them up |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Wedding Cake | Wedding Cake | Ask the baker how they display the cake – for instance is it on an UGLY doily? If you don't like doilies then find out what other alternatives are. |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Bride | Go have your first fitting a soon as your dress arrives. Schedule alternations |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Welcome Baskets | Design the “Welcome Baskets” that guests will receive when checking into hotel (what they will look like, what will be in them) | Design and Create | Signage |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Guest Book | Assign someone the task of monitoring the guest book during the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Powder Room Basket | Assign someone the task of bringing the Powder Room Baskets home after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Beauty/Hair/Makeup | Hair | Make appt. to take your veil to your hairstylist to make sure it will work with your current hair style choice | Attend/Make Appt. | Hair |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Placecards | Assign someone the task of taking the placecards to the reception site and putting them out |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Dress/Tux/Bridal Party | Flowergirl | Select your flowergirl's accessories (jewels, etc). This is traditionally a gift you can give her. |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Table Names/Numbers | Print/Order/Make Table Names/Numbers |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Wedding Cake | Wedding Cake | Finalize wedding cake design |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Favors | Assign someone the task of bringing the left-over favors home after the wedding |  |  |  |  | NO
Phase 2: Becoming Real | 1-3 Months To Go! | Decor/Invitations/Programs/etc. | Ceremony Programs | Print/Order program | Design and Create | Program |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Schedule/Plan-o-Gram/Seating | Seating Chart | Send caterer the final seating chart including menu selections (if applicable) |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Roles for People |  | Call or email the bridal party to relay all important information related to rehearsal and wedding (dates, times, transportation, duties, etc...) |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Welcome Baskets | Box up the Welcome Baskets for someone to take to the hotel |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Table Names/Numbers | Box up the Table Names/Numbers for someone to take |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Roles for People |  | Provide each member of the wedding party with detailed schedule of events for the wedding day |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Roles for People |  | Provide list of duties to Maid of Honor & Best Man | Design and Create | Bridal Party |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Wedding Rings | Wedding Rings | Pick up wedding bands and make sure the inscription is correct before leaving store | Buy/Shop | Rings |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Venue | Venue | Call location manager to make sure vendors have access to location when they need it |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Schedule/Plan-o-Gram/Seating | Timeline | Finalize your ‘day of’ schedule/timeline and share with attendants, parents, coordinator, and all vendors |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Hotel for Guests/Wedding Night | Wedding Night | Confirm Hotel Reservations for Wedding Night |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Wedding Invitations | Wedding Invitations | Contact guests who have not RSVP’d |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Disposable Cameras | Box up the cameras for someone to take |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Unity Candles | Box up the Unity Candle for someone to take |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Signage | Box up the Signage for someone to take tot he ceremony/reception/hotel |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Photo Displays | Box up the Photo Displays for someone to take |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Rehearsal and Rehearsal Dinner | Ceremony Rehearsal | Confirm Rehearsal Times with Officiant |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Beauty/Hair/Makeup | Dentist | Go for a teeth cleaning. Finish up all whitening services (if applicable). | Attend/Make Appt. | Health/Wellbeing |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Honeymoon | Honeymoon | Confirm honeymoon and travel arrangements |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Hotel for Guests/Wedding Night | Hotel for Guests | Confirm reservations for out-of-town guests | Confirm | Hotle |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Rehearsal and Rehearsal Dinner | Ceremony Rehearsal | Make sure eveyone knows where the ceremony rehearsal is (if different than where the dinner is) |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Guest Book | Box up the Guest Book for someone to take | Confirm | Wedding Accessories |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Videographer | Videographer | Confirm location, date, and time with videographer |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Dress/Tux/Bridal Party | Bride | Attend final dress fitting |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Seating Chart | Give seating chart to caterer or location manager |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Centerpieces | Box up the Centerpieces for someone to take |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Gift Registry | Gift Registry | Check that there are enough options left on your registry | Confirm | Registry |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Hotel for Guests/Wedding Night | Hotel for Guests | Confirm final reservations (you'll need this info in case you want to provide welcome baskets, etc) |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Dress/Tux/Bridal Party | Bride | Confirm the delivery date or pick-up date for your gown | Confirm | Wedding Dress |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Beauty/Hair/Makeup | Hair | Confirm Hair appointments |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Ceremony | Ceremony | Email/Mail/Pass a copy of the program to the officiant so they know how you want it to work in advance | Confirm |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Powder Room Basket | Box up the Powder Room Basket for someone to take |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Dress/Tux/Bridal Party | Bridesmaids | Confirm with your gals that everyone has their dresses and they fit, etc. | Confirm | Wedding Dress |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Caterer | Caterer | Give final head count to caterer; confirm set-up instructions and menu items |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Photography | Photography | Confirm location, date, and time with photographer; give them a must-take photo list. |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Ceremony Programs | Box up the Programs for someone to take |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Schedule/Plan-o-Gram/Seating | Plan-o-Gram | Send caterer the plan-o-gram |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Music | Music | Confirm reservation with band – confirm they've received play songs and they know when and where they should set-up at the venue. |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Payment | Payment | Confirm all final payment amounts with vendors |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Bridal Luncheon | Bridal Luncheon | Confirm plans for bridal luncheon (reservations, catering, etc) |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Ring Pillow | Box up the Ring Pillow for someone to take |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Seating Chart | Finalize seating chart for guests at reception | Plan | Seating Chart |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Favors | Box up the Favors for someone to take |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Decor/Invitations/Programs/etc. | Rentals | Confirm delivery times/method for rental items |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Beauty/Hair/Makeup | Makeup | Confirm Makeup appointments |  |  |  |  | NO
Phase 3: OMG – So much to do! | 2 Weeks To Go! | Limo | Limo | Confirm reservations and get transportation providers a schedule and addresses for pickups on wedding day |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Beauty/Hair/Makeup | Hair | Get your hair colored and trimmed |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Decor/Invitations/Programs/etc. | Placecards | Box up the Placecards for someone to take with instructions that include the seating chart | Assign to Vendor | décor | Kerri will do |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Wedding Cake | Wedding Cake | Take special ribbon or decorations you want on the cake to the baker | Attend/Make Appt. |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Caterer | Caterer | Take items to the caterer that they have offered to set up for you (Centerpieces, etc) |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Ceremony | Ceremony | Determine ceremony seating for special guests (give list to ushers) |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Caterer | Caterer | Give final attendance numbers to caterer and confirm all plans |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Bridal Luncheon | Bridal Luncheon | Have the Bridal Luncheon |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Hotel for Guests/Wedding Night | Hotel for Guests | Reconfirm accommodations for out-of-town guests |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Beauty/Hair/Makeup | Hair | Re-Confirm all Hair appointments |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Schedule/Plan-o-Gram/Seating | Timeline | Inform all vendors of any changes |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Decor/Invitations/Programs/etc. | Rose Petals | Assign vendor to arrange rose petals for ceremony | Assign to Vendor | Rose Petals | Kerri will do |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Gifts for People | Gifts for People | Get a sweet card for your hubby for the day-of |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Dress/Tux/Bridal Party | Bride | Pick up wedding dress from bridal salon (can do this a day or two before). Make sure you have a place to hang it to avoid wrinkles. |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Ceremony | Ceremony | Meet with officiant to finalize ceremony including attendant formations | Attend/Make Appt. | Ceremony |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Gift Registry | Gift Registry | Check that there are enough options left on your registry | Confirm | Registry |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Beauty/Hair/Makeup | Makeup | Re-Confirm all Makeup appointments |  |  |  |  | NO
Phase 4: AUGHHHHH! | 1 Week To Go! | Wedding Cake | Wedding Cake | Confirm head count, delivery time, and location with baker |  |  | Kerri |  | NO
Phase 5: I am SO ready | Day Before | Dress/Tux/Bridal Party | Groom | Pick up groom’s attire, make sure it fits and gather all accessories (be sure to try it on….don’t wait until the day-of to do this!!) |  |  |  |  | NO
Phase 5: I am SO ready | Day Before | Limo | Limo | Re-confirm limo reservations, pick-up times, addresses, etc. |  |  |  |  | NO
Phase 5: I am SO ready | Day Before | Ceremony | Ceremony | Have a rehearsal with everyone involved in the ceremony |  |  |  |  | NO
Phase 5: I am SO ready | Day Before | Ceremony | Ceremony | Review ceremony seating with ushers at rehearsal |  |  |  |  | NO
Phase 5: I am SO ready | Day Before | Dress/Tux/Bridal Party | Bride | Pull together wedding gown, veil, shoes, stockings, and a last-minute emergency kit (aspirin, makeup, safety pins, mints, etc..) |  |  |  |  | NO
Phase 6: I'm a MRS!!!! | Day of | Partae – like a Rock Star! | Party like a Rock Star! | Start making babies... |  |  |  |  | NO
Phase 6: I'm a MRS!!!! | Day of | Partae – like a Rock Star! | Party like a Rock Star! | Get married, party,and have a blast, gal! |  |  |  |  | NO
Phase 6: I'm a MRS!!!! | Day of | Ceremony | Ceremony | Have bestman/maid of honor take the marriage certificate home with them for safe keeping |  |  |  |  | NO
Phase 6: I'm a MRS!!!! | Day of | Thank You's and Gifts | Gifts | Assign someone the task of bringing home your gifts after the wedding |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Payment | Payment | Make sure all vendor bills have been paid |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Thank You's and Gifts | Thank You's | Within two months of your wedding set aside some romantic evenings to write that stack of Thank You notes |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Videographer | Videographer | Find out when you can expect your edited wedding video (if you used a videographer) |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Photography | Photography | Take any film to be developed (these will be the first photos available since most photographers can take weeks) |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Caterer | Caterer | Go pick up (of have someone do it for you) items that the caterer brought home for you |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Wedding Cake | Wedding Cake | Freeze the top layer of the wedding cake to be eaten on your first anniversary |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Dress/Tux/Bridal Party | Bride | Take gown and veil to be cleaned (or have someone do it for you). Assure cleaner is experienced in cleaning wedding gowns |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Gifts for People | Gifts for People | Write a thank you for each vendor (That did a good job of course) and send it to them before departing to the honeymoon. |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Thank You's and Gifts | Thank You's | Keep a careful record of all gifts received (write thank you notesimmediatelyto save time when you get back) |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Gifts for People | Gifts for People | Tell your parent's/family who helped thank you. |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Decor/Invitations/Programs/etc. | Floral Preservation | Take the bridal bouquet and other wedding mementos to be preserved (if you are a true sentimentalist) |  |  |  |  | NO
Phase 7: No! It can't be over!!! | Day After | Dress/Tux/Bridal Party | Bride | Arrange for someone to pick up your wedding dress and other personal belongings after you depart |  |  |  |  | NO